## Story Points
Role | # | User Story | Pts | Justification
Developer | D1 | As a developer, I want the backend to cache responses and manage rate limits, so the terminal stays within provider quotas and responds faster. | 8 | New backend service; cache with TTL + per-provider throttling. Depends on backend existing.
| D2 | As a developer, I want the backend to normalize provider responses into the shapes each module expects, so the frontend needs no changes when going live. | 8 | Map 4 providers' differing formats to each module's contract; touches every data module.
| D3 | As a developer, I want the frontend to remain one HTML file with no build step, so the terminal stays portable download, double-click, run. | 2 | A constraint to uphold rather than new work; low effort but requires discipline.
| D4 | As a developer, I want all colors and typography routed through CSS custom properties, so I can retheme by changing a handful of values. | 3 | One-time token refactor; mechanical but spans the whole stylesheet.
| D5 | As a developer, I want to receive alerts if anything goes wrong on the user's end. | 8 | Client error capture + a transport off the user's machine; implies a logging endpoint/backend. High uncertainty.
Developer subtotal |  |  | 29
User | U1 | As a user, I want to open the terminal by double-clicking one file, so I can start with no install, server, or setup. | 1 | Already the architecture's default; essentially free.
| U2 | As a user, I want to switch modules from the top navigation, so I can move around quickly without losing my place. | 2 | switchModule() router already exists; standard pattern.
| U3 | As a user, I want a live grid of 25+ assets across multiple classes, so I can watch the whole market on one screen. | 5 | Multi-asset fetch, interval refresh, conditional formatting, sizable render.
| U4 | As a user, I want to view bid/ask depth for a selected symbol, so I can gauge liquidity before acting. | 5 | Order-book ladder render + per-symbol refetch; moderate logic.
| U5 | As a user, I want a consolidated news and macro feed, so I can keep context on what's moving prices. | 3 | Mostly a formatted list; light derivation.
| U6 | As a user, I want an overview of portfolio exposure and key risk metrics, so I can understand my risk in one place. | 8 | Aggregation across positions, several computed risk metrics, KPI + chart.
| U7 | As a user, I want to model P&L for common strategies, so I can see the payoff before entering a position. | 8 | Black-Scholes pricing, 8 strategy templates, interactive payoff diagram.
| U8 | As a user, I want to test an allocation against a benchmark, so I can judge its historical risk-adjusted performance. | 8 | Time-series engine; Sharpe/Sortino/Calmar; equity + drawdown charts.
User subtotal |  |  | 40
Customer Support | C1 | As customer support, I want a help panel explaining what each module does, so I can understand the terminal without external docs. | 3 | Static content surface + reachable control; effort is writing 29 descriptions.
| C2 | As customer support, I want a clear, specific message when a module can't load live data, so I know it's a data issue, not a broken terminal. | 3 | Per-module error-state handling + notice; contained but spans modules.
| C3 | As customer support, I want to export a diagnostic snapshot (browser, version, console errors, failed modules/providers), so I can share it when reporting a problem. | 5 | Collect version/browser/errors/failed providers, format, redact secrets; capturing console errors cleanly adds uncertainty.
| C4 | As customer support, I want to see the terminal's version, so I can check I'm on the latest file and reference it when asking for help. | 1 | A version string in the footer; trivial.
| C5 | As customer support, I want a check of whether each data provider is configured and reachable, so I can self-diagnose why a module isn't loading. | 5 | Per-provider reachability test distinguishing not-set / unreachable / rate-limited.
| C6 | As customer support, I want a ticketing system so when a user has a problem I can either solve it or send the ticket to the developer. | 13 | Full ticketing layer: capture, store, assign, route, escalate, statuses — needs backend + persistence + UI. Largest item.
Customer Support subtotal |  |  | 30
GRAND TOTAL |  |  | 99